## Glossary
Forward Works – Glossary of Table Headings Expected Market Entry (FY Quarter) The anticipated financial quarter in which the project is expected to be released for pricing or formal engagement.
Delivery Stream Allocation Indicates the procurement stream the project falls under based on Watercare’s published strategy: • Discrete Projects • Asset Upgrades & Renewals • Major Projects
PDG Categorisation Categorisation of the project as per Watercare’s Programme Delivery Group (PDG) framework, indicating project scale, complexity, and governance pathway.
Phase The phase of the project (e.g., Feasibility, Design, Execution, Closure) is aligned with the Watercare Project Lifecycle. For clarity, only the Design and Execution phases are shown.
Project ID A unique identifier is assigned to each project. Prefixes indicate service type: • WA = Water • WW = Wastewater
Project Name The working title of the project as recorded in internal systems.
Project Description A short, high-level summary of the project's purpose or scope (sourced from Watercare’s internal project database). Some descriptions may be pending and will be progressively updated in future releases.
Project Value Range Estimated total project cost grouped into indicative financial value bands.
Intended Allocation Indicates Watercare’s current planning approach for procurement: • Within Panel – likely to be delivered via an existing panel Framework agreement • Outside Panel – likely to be competitively tendered either closed or open market
Note: This column is for visibility only and does not represent a final allocation decision.

## FW Update 251124
WATERCARE FORWARD WORKS - PANEL UPDATE | [7 empty] | Release Date: 24/11/2025
Note: Data reflects the most recent reporting cycle and may be subject to updates based on ongoing assessments and project developments. Excludes Large Programmes, Flood, TARP projects. Q1: 1 July - 30 September Q2: 1 October - 31 December Q3: 1 January - 31 March Q4: 1 April - 30 June
Expected Market Entry by Financial Year Quarter | Delivery Stream Allocation | PDG Categorisation | Phase | Project ID | Project Name | Project Description | Project Value Range | Intended Allocation
FY26 Q2 | Asset Upgrades & Renewals | Electrical | Design | SS0001069 | Networks PS Electrical Upgrade | Electrical Upgrades at 6 Pump Stations in the Northen Network WWPS | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Electrical | Design | WA0001734 | WPTIT Soft Starter Replacements | Replace aged Soft Starters at Titirangi PS | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Electrical | Execution | SS0001027 | Rain Gauge Earthing Issues | The project is to upgrade the rain gauge installations at 30 dams. There have been multiple equipment failures associated with solar powered rain gauge sites. Initial investigations indicate this is likely due to a lack of proper earthing and surge protection being applied. There are concerns that these installations may not meet the requirements of the electrical regulations and a review and certified design is required. | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WW0001114 | DTMAN Switchboard Replacements | The project is to replace 16 switchboards at Mangere WWTP in power building and IPS areas due to age and condition. | 10 - 20 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WW0001301 | Northern Networks Control Upgrade | The project is to upgrade the following electrical equipment at the 3 Northern Networks pump stations- Switch boards, VSDs and Controls systems. | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001800 | DTARB UV Upgrade | The scope of DTARB UV Upgrade, referred to within the Army Bay WWTP Upgrade Project as Early Works, will support compliance to the consented effluent quality at Army Bay Wastewater Treatment Plant (WWTP). This will be achieved with the upgrade of the UV System including installation of a second UV channel and additional electrical equipment within an expansion of the existing UV Electrical Building. | 3 - 10 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001812 | Mangere WWTP IPS1 & Hydraulics Upgrade |  | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001816 | Mangere WWTP Renewals - PD | This project is a three-year renewals programme at the Māngere Wastewater Treatment Plant (WWTP), delivered in annual work packages from FY26 to FY28. The scope includes the renewal or refurbishment of critical assets identified through condition assessments and risk analysis, prioritising those with the highest operational, environmental, and safety risks. | 20 - 30 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001819 | Rosedale WWTP Renewals - PD | DTROS WWTP FY26-28 Renewals Programme of high risk assets. | 20 - 30 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001804 | Hingaia WW Storage Solution | The existing Hingaia wastewater pumping station is already at capacity. The current population projection indicates that additional flow from the future developments will exceed existing capacity of the Hingaia pumping station in the near future and increase the risk of wastewater overflow into the environment. In order to allow for the developments to continue an additional storage capacity needs to be provided until an interim Hingaia pumping station upgrade will be completed. The new storage tanks will provide a temporary solution to service growth in the Southern Growth Area (SGA) until interim upgrade of the existing Hingaia wastewater pumping station will be completed. It will also increase resilience by providing required emergency storage for the interim Hingaia pumping station. | 20 - 30 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001824 | FY26 Transmission Sewer Renewal | FY26 Transmission Sewer Renewals is a program of works which will deliver renewed and rehabilitated Transmission wastewater assets that are in poor condition or approaching their end of service. Packages will be identified and scoped through the Planning team and delivered through Capital Delivery. | 3 - 10 Million | outside panel
FY26 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001826 | FY26 Local Wastewater Network Renewals | FY26 WW Renewals is a program of works which will deliver renewed and rehabilitated local network wastewater assets that are in poor condition or approaching their end of service. Packages will be identified and scoped through the Planning team and delivered through Capital Delivery. | 10 - 20 Million | outside panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001495 | Mt Hobson PS Upgrade | Mt Hobson PS Upgrade • Pumps nearing end of lifetime and currently not meeting system demand. • Main risks are the current pump failing and the challenges around the constructability phase of project. • Current scope only includes pump station upgrade. Upstream and downstream are out of scope. • SCADA data and modelling results show the pumps are undercapacity for current demand. • Pump upgrade required to meet both current and future demands. | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001073 | West Boost Pumping | Construct a transmission water pump station to boost supply up to 90ML/D to the Titirangi and future Woodlands Reservoirs and western supply area. To be constructed at 119A May Road. | 20 - 30 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001746 | Tarapuka Road Watermain | • The existing watermain for this section of the development has been installed in the wrong alignment. • This section of the watermain needs to be aligned with north and south sections. • Once completed, this watermain will service the developments on the west side of Fred Taylor Drive. • The watermain needs to be operational to service the new school, which is being constructed and anticipated to be commissioned in FY26. • The developers are responsible to deliver the other of the watermain | < 3 Million | within panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001767 | FY26 Transmission Watermain Renewals |  | 10 - 20 Million | outside panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001768 | FY26 Local Network Watermain Renewals | This project involves the proactive renewal of approximately 14km of asbestos local network watermains. The sites have been selected across the north, south, west and east areas of the Auckland region. This project is the next stage of a ten year proactive network watermain renewal programme. | 20 - 30 Million | outside panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001775 | Onehunga CI Watermain Stage 1 Renewals | The project entails the replacement of 4.15km of cast iron network watermains in the Forbes St and Spring St in the Onehunga Water Supply Zone. These renewals target the area adjacent to the Onehunga Water Treatment plant which is programmed to be recommissioned. | 10 - 20 Million | outside panel
FY26 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001776 | Whangaparaoa Rd Watermain Renewals | This project entails the replacement of 1.5km of PE network watermain that has failed in Whangaparaoa Rd, Hibiscus Coast. The new watermain will consist of PE installed by the directional drilling technique. The aim is to improve water security in the Vipond Marellen and D'Oyley Water Supply Zones. | 3 - 10 Million | outside panel
FY26 Q2 | Discrete Projects | Discrete Projects | Execution | WW0001092 | Otara Catchment WW Capacity Upgrades | The Ōtara Wastewater Network Capacity Upgrades Project aims to reduce the amount of wastewater that enters the environment due to overflows from the Ōtara Branch Sewer (DSOTB), easing existing capacity constraints and allowing for higher density development in the Ōtara Catchment. This will be achieved by intercepting and diverting wastewater from the existing Ōtara Branch Sewer to a new wastewater pump station from where it will be pumped via a new rising main to the existing Ōtara Pump station (DPOTB) at Billington Reserve. | 50 - 100 Million | within panel
FY26 Q2 | Discrete Projects | Discrete Projects | Execution | WW0001686 | Dunkirk Stage 2 Rising Main | The Dunkirk Wastewater Upgrade Project was developed to meet the planned growth in Tamaki, to ensure that Watercare continues to efficiently and effectively manage levels of service (LoS) to our customers and minimise adverse impact on local receiving environments. This project comprises of three distinct stages, delivering a new wastewater pumpstation, bulk and local wastewater network upgrades. | 10 - 20 Million | within panel
FY26 Q3 | Major Projects | Major Projects | Design | WW0001474 | Mangere WWTP Distributed Blowers | To decentralise blowers to increase resilience of the system (currently single point of failure to 9 reactors out of 11), to replace existing blowers and service 3 reactor clarifiers. | 100 - 250 Million | outside panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001328 | Silverdale West Water Servicing Phase 3 | The project aims to complete the design and construction of the Orewa 1 to 3 cross section along with a new BSP at John Fair Drive road to supply the Wainui and Silverdale West developments. Additionally BSP standards will be updated as part of this project. | 3 - 10 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001378 | DTROS Fire Systems Upgrade | Fire Protection System Upgrade at Rosedale WWTP | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001391 | STWKO Fire Protection Upgrade | Fire protection upgrade at Waikato WTP | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001412 | STHUI FW flowmeter replacement | XXX117 - Huia WTP FW flow meter replacement (MH) - | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001730 | STWEL Switchboard Replacement | Urgent replacement of switchboard at Wellsford WTP due to safety and resilience concerns | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001731 | STHEL Standby Generator | Backup generator for Helensville WTP | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001735 | STWKO VSD Replacements | Replace small VSDs at Waikato WTP due to age and obsolescence | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WA0001736 | STARD Filter PIT & FIT Replacements | Replacement of pressure and flow instruments on filters at Ardmore WTP due to condition observed during Condition Assessment rounds | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WW0001218 | Wastewater Transmission VSD Upgrades | Replace aged Variable Speed Drives at a number of WWPS | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WW0001766 | DTMAN Switchboards Replacement FY25 | Replacement of six HV and six LV switchboards at Mangere WWTP | 10 - 20 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WW0001767 | FY25 Wastewater PS Elec Replacements 2 | Replacement of switchboards at 10 WWPS | 3 - 10 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Design | WW0001768 | FY25 Wastewater PS Elec Replacements 1 | Replace switchboards at 11 WWPS | 3 - 10 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WA0001639 | STARD Turbidity Instrument Replacements | Replace filter turbidity instruments due to age and obsolescence of current models | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WA0001734 | WPTIT Soft Starter Replacements | Replace aged Soft Starters at Titirangi PS | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WW0001492 | DTROS Electrical Resilience MLE/PST | Dividing up process loads across multiple switchboards for greater resilience. PST 5 and 6 loads to be transferred to New PST 7 Switchroom. Clarifier and RAS 3&4, MLE 3 loads to be transferred to New MLE 4 Switchroom | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WW0001558 | Rosedale WWTP Fire Main Installation | Extend existing 150mm main and install two new hydrants | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WW0001668 | Wairau Valley Pumpstation Drives | Project mitigates the largest impact from flow surging to the treatment plant. Installing new VSD to drives reduces surges from 0.4m3/s pumps start ups. VSD will allow flows to ramp up & down instead of off/on. VSD to be located in attached storage area and Incorporated cable harness arrangement to simplify removal of pumps with integrated cables (Improvement basis from Fred Thomas PS project). Storage room to be protected from flood events up to 1in100 years through a barrier to the roller door and floor door to replace the pedestrian door. This is aligned with the current development of flood protection to the main pump station building. | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WA0001455 | MOH Regional Fluoride Dosing | MOH Regional Fluoride Dosing WA0001455 The W50 Water Treatment Plant (WTP) is expected to remain operational until the new Waikato A WTP is commissioned in 2034. Under the Health (Fluoridation of Drinking Water) Amendment Act 2021, Watercare must fluoridate the Auckland metro supply (0.7–1 mg/L). A dedicated fluoride dosing system is required at W50 due to consistently low treated water fluoride levels (<0.7 mg/L). Additionally, the W50 WTP lacks resilience, as it cannot supply fluoridated water when the Waikato WTP is offline. This project aims to install a fluoridation system at W50 in compliance with the legislation. | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001142 | Rosedale WWTP Biogas & Co-Gen Expansion | This project provides Rosedale WWTP with an additional co-generation engine to increase utilization of biogas production in on-site electricity generation and reduce the sites grid electricity consumption. This project also shall increase the capacity and resilience of the biogas treatment system to cater for thermal hydrolysis circa 2031. | 10 - 20 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001387 | Rosedale MP biogas Piping | Replace blowers and medium pressure biogas underground piping to engine. Includes new blowers and second smaller flare. Approx size 750Nm3/h | 3 - 10 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001486 | Mangere Small Biofilter Media Replacement | Asset renewal of biofilter | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001214 | Kahika Pump Station Upgrades | This project is to raise the level of service within the Kahika catchment. This consists of increase the peak pump rate of Kahika Pump Station from 320 litres per second to 500 litres per second and a new Rising Main into Wairau Sewer Branch. | 20 - 30 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001130 | Hingaia Watermain East/West | The Southern Growth Area (SGA) encompassing Hingaia, Drury, Auranga, Opaheke and Paerata is due to undergo significant growth over the next 20 years. Approximately 6,000 lots (18000 PE)for the SGA are predicted to be developed by 2025. This watermain is required to be completed and in service before the SGA development reaches 5,600 lots (~2025), to ensure levels of service can be maintained in the area. Once complete, the HEW watermain will provide two feeds to the Hingaia Peninsula and Auranga developments providing network resilience through redundancy. | 10 - 20 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001333 | Market Road Watermain Replacement |  | 3 - 10 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001747 | Mangatangi Dam Bypass FCV Replacement | Replacing the Flow control valve within the Mangatangi Dam valve tower. | < 3 Million | within panel
FY26 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001756 | Establishment of Permanent Tanker Filling station | Development of a new permanent tanker filling station (TFS) in Huapai to replace the existing temporary TFS at 18 Oraha Rd. The tankers that will be refilled at this station are to service properties in Kumeu, Huapai, and surrounding areas isolated from the water network and reliant on rainwater tanks. | 3 - 10 Million | within panel
FY26 Q3 | Discrete Projects | Discrete Projects | Design | WA0001343 | Wesley/Paerata Watermain | This transmission watermain has two fundamental needs: - provide a cross connection between Waikato No.1 WM and Waikato No.2 WM. - provide a transmission supply to the north of Pukekohe where the Paerata WSZ can be supplied from to service growth in the Wesley/ Paerata area over the next 50 years. By 2028, the population in Paerata is forecast to grow by +13650 PE vs 2018 levels, and then by a subsequent +5400 PE by 2038. This watermain upgrade will provide capacity to provide for the full +19150 PE growth in the region. Further, the line provides resilience to the existing network by providing redundancy. | 50 - 100 Million | within panel
FY26 Q3 | Discrete Projects | Discrete Projects | Design | WW0001026 | Forrest Hill WW Catchment Diversion | The Forrest Hill wastewater trunk network is currently undersized causing uncontrolled wet weather spills within several private residential properties. This project creates additional capacity to relieve these overflows. | 30 - 50 Million | outside panel
FY26 Q3 | Discrete Projects | Discrete Projects | Design | WW0001446 | Paerata Wastewater Servicing | Upgrade of the existing Te Paea Pump Station, construction of a new Paerata Pump Station, and installation of a rising main linking both to the Isabella North Pump Station. The works will improve capacity, reliability, and future-proof wastewater conveyance for growth in the area. | 50 - 100 Million | within panel
FY26 Q3 | Discrete Projects | Discrete Projects | Execution | WW0001565 | Mangere WWTP Svi Improvement Upgrade | Installation of InDense hydrocyclone technology on RCs 7-9 at Mangere WWTP to increase settleability by improving the Sludge Volume Index (SVI). | 10 - 20 Million | outside panel
FY26 Q3 | Major Projects | Major Projects | Design | WW0001112 | Army Bay WWTP Upgrade | The existing Army Bay WWTP has a capacity of around 14.0 MLD (average dry weather flow, ADWF). Whereas its served catchment areas currently have an ADWF of about 13.7 MLD. It is currently limiting the housing development in the catchment areas. In addition, the newly granted resource consent has more stringent treated wastewater quality requirements that the existing WWTP cannot meet. The Army Bay WWTP Upgrade will follow the staging approach defined in the new resource consent (i.e. Stage 1 upgrade increases the capacity to 22.5 MLD (ADWF) while complying with the consented quality requirements), and thereby to enable accepting new connections and complying with the new resource consent. | 100 - 250 Million | outside panel
FY26 Q4 | Asset Upgrades & Renewals | Electrical | Design | WA0001732 | FY25 Water PS Elec Replacements 2 | Replace switchboards at three water PS (WPCBL, WPONL, WPRED) Note: WPRED now excluded as already upgraded under a different project | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Electrical | Design | WA0001733 | FY25 Water PS Elec Replacements 1 | Replacement of switchboards at three WPS (WPWCR, WPWKE, WPSUN) Note: WPSUN now excluded as already replaced under another project. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Electrical | Execution | WA0001391 | STWKO Fire Protection Upgrade | Fire protection upgrade at Waikato WTP | < 3 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Electrical | Execution | WA0001412 | STHUI FW flowmeter replacement | XXX117 - Huia WTP FW flow meter replacement (MH) - | < 3 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WA0001714 | Huia WTP Sludge Processing Capacity Improvements | Huia WTP Sludge Processing Capacity Improvements Maintaining production capacity and increasing resilience of the almost 100-year-old existing Huia water treatment plant (WTP) is essential for the business until new infrastructure is built to replace the existing plant. Several recent large storm events indicated that a key bottleneck at the treatment plant is the sludge handling capacity, specifically after storm events. This is due to the higher turbidity levels observed from the inflow stream, which has significantly increased the volume of sludge produced. The aim of this project is to increasing the sludge processing capacity and improving resilience of the solids handling process at the Huia WTP. In so doing this project assesses the options to increasing centrifuge capacity and resilience. It also investigates the viability of addressing the sewer network capacity limitations. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001107 | Waitakere WTP Interim Upgrade | The aim of this project is to upgrade the chemical facilities at the Waitakere Water Treatment Plant (WTP) to ensure compliance with the regulations and standards. The upgrade will minimise health and safety risks, improve operability and resilience. a) Aluminium Sulphate (Alum): Construct a new storage and dosing system and decommission the existing system b) Lime: Construct a new slurry makeup, storage, and dosing system, and demolish the existing system. c) Hydrofluorosilicic Acid (HFA): Replace the bulk tank, construct a new storage and dosing system, and decommission the current system. d) Chlorine Gas: Modify the existing drum room by replacing the door and extending the gantry. e) Powdered Activated Carbon (PAC): Add a new big-bag unloading and slurry makeup system while retaining the existing storage and dosing system. f) Polymer: Construct a new storage and dosing system for raw water treatment and modify the existing polymer system. g) Decommissioning and Demolition: Remove outdated systems (Alum, Lime, HFA, and polymer) and reinstate the areas. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001712 | Waikato WTP CSEU Stage 2 | Upgrade of existing chemical storage and dosing systems at the WTP, including removal of old hypo, alum, lime, and HFA tanks. To installation of new alum and HFA storage tanks, upgraded chemical delivery bay, bund conversions for HFA and washdown containment. The project is required to ensure reliability and resilience of operation of the Waikato WTP up to 175MLD and comply with the latest H&S regulations. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001465 | Biogas Drier Replacement And Standby Unit | Monday 2025-08-04_WW0001465 - Biogas Drier replacement and standby unit addition. This project is part of the wider Biogas system upgrades at Mangere WWTP. This project includes the demolition of the decommissioned LP Gas holder, constructing new concrete plinths and installing two new skid-based Biogas conditioning units. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001485 | Rosedale WWT CAS Tank Renewal - Peak Flow | This project is to increase resilience during peak flows and cater for growth. This consists of renewing the convectional activated sludge tank. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001500 | Rosedale WWTP Centrifuge 3 Upgrade | This upgrade and renewal project will increase the centrifuge’s capacity from 8m3/hr to 17m3/hr, increasing total plant processing from 50m3/hr to 59m3/hr. It will also increase dewatering resilience and provide for growth until the implementation of thermal hydrolysis (delivery circa 2030). The replacement of Centrifuge 3 will ensure that the dewatering process can operate efficiently and provide the necessary process resilience. Effective dewatering will reduce the amount of biosolids that go to landfills, reducing the impact on the environment and lowering disposal costs. Replacing Centrifuge 3 with a larger unit will increase dewatering capacity, provide the necessary resilience and support growth in the catchment. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001800 | DTARB UV Upgrade | The scope of DTARB UV Upgrade, referred to within the Army Bay WWTP Upgrade Project as Early Works, will support compliance to the consented effluent quality at Army Bay Wastewater Treatment Plant (WWTP). This will be achieved with the upgrade of the UV System including installation of a second UV channel and additional electrical equipment within an expansion of the existing UV Electrical Building. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001460 | Otara local network upgrade | The project requires an upgrade of the wastewater network that is serving Otara, Papatoetoe and part of Flat Bush catchments (Otara and Otara East branch sewer catchments) and will form part of the long term solution to accommodate increased growth and development in these catchments. | 50 - 100 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001798 | Waiuku WW Network diversion | This project involves installing two diversions in the Waiuku Wastewater Network to address capacity constraints in the ageing infrastructure of the wastewater network at Waiuku golf course. | < 3 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001780 | Southwest Interceptor Renewal | In October 2024, $2,500,000 to make safe 140m of the Southwestern Interceptor located inside the Mangere WWTP site following two successive failures that occurred after the 2023 flooding events. A subsequent business case to design and construct the permanent solution was approved in July, taking the total capital expenditure approval to $31.7m. | 30 - 50 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001783 | Clonbern Rd WW Diversion | The Clonbern Rd WW Diversion project seeks to address a local networks sewer line that is currently in poor condition, identified in 2021. The Concept Design has been completed and proposes a new sewer line through the road corridor and includes rehabilitation of the existing sewer line to continue serving the property connections. Flows will be diverted upstream of the failed line in to the new sewer asset and connect back in via MH34 of the Branch 1 Remuera Line | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001416 | Mission Heights PS - Upgrade | XXX124 - Mission Heights PS - Upgrade - - 15 Years old - need to review Brendon's work | < 3 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001417 | Pleasant Rd PS Replacement | WW0001417 - The Pleasant Road Pump Station (PRPS) Replacement project addresses the end-of-life renewal of a critical water infrastructure asset serving West Auckland. Originally designed to boost flow from the Huia 2 Watermain to the Waitakere Reservoir, the station was repurposed in 2023 following flood-related damage to instead supply the Highland Avenue Bulk Supply Point (BSP). This change eliminated its dual-supply function, reducing network resilience. This project will deliver feasibility and concept design for: A new dual-pump configuration within a single building—one set dedicated to the Highland Ave BSP, and one to the Waitakere Reservoir via the Waitakere 1 Watermain. Enhanced supply resilience and operational flexibility during network failures or planned outages. Capacity upgrades to support future growth and shutdowns at the Waitakere WTP and raw watermain. Consideration of new site acquisition due to existing spatial constraints. The upgrade will restore critical redundancy, support ~15,000 residents, and strengthen West Auckland's water supply resilience. | 10 - 20 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001526 | Waikumete Pump Station (Sunnyvale PS) | Implementation of a boosted supply zone via a new Pump Station to be constructed next to the Waikumete Reservoir. | 3 - 10 Million | within panel
FY26 Q4 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001747 | Mangatangi Dam Bypass FCV Replacement | Replacing the Flow control valve within the Mangatangi Dam valve tower. | < 3 Million | within panel
FY26 Q4 | Discrete Projects | Discrete Projects | Design | WA0001041 | Hunua 2 Watermain (Ti Rakau Bridge) | The existing Hunua 2 pipe bridge at Pakuranga Creek/Ti Rakau Drive is in poor condition and requires significant repair or replacement to maintain resilience of supply. | 30 - 50 Million | within panel
FY26 Q4 | Major Projects | Major Projects | Execution | WW0001045 | Hingaia Wastewater Servicing Scheme | This project caters for growth in the Hingaia Peninsula Drury and Opaheke areas and will reduce wastewater overflows to Pahurehure Inlet and Manakau Harbour by diverting flows from the Southern Interceptor to the South Western Interceptor. Installation of two additional emergency storage tanks at the existing Hingaia PS with a total volume of 450 cubic metres. Package 2 Upgrade of the existing Hingaia PS from 100L/s to 270L/s installation of a DN630 rising main 8.3km in length break pressure chamber and gravity main conveying flows from Hingaia PS to Manurewa South PS. | 100 - 250 Million | outside panel
FY27 Q1 | Asset Upgrades & Renewals | Civil & Construction | Execution | WA0001509 | Waiuku Reservoir Upgrades | The project aims to increase water storage capacity in the Waiuku area by constructing an additional water reservoir at the Waiuku Road Water Treatment Plant (WTP) site. The scope includes: • New approximately 1.5ML concrete reservoir located next to the existing Waiuku Reservoir. • A branch on the existing UV outlet connecting to the new reservoir. • Branch connection to the existing DN355 supply / feed pipeline. • Scour and overflow connection from new reservoir to existing reservoir waste system. • A retaining wall system around the new reservoir to achieve the same base reference level with the existing reservoir. • Future tie-ins to the reservoir’s inlet and outlet to connect with the future centralised Waiuku WTP system. | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Electrical | Design | WA0001658 | Mt Roskill Reservoir RTS | Mt Roskill Reservoir - Feasibility Study - investigation to check the viability of getting this reservoir back to service and provide concept design. | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Electrical | Execution | WA0001378 | DTROS Fire Systems Upgrade | Fire Protection System Upgrade at Rosedale WWTP | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Electrical | Execution | WA0001736 | STARD Filter PIT & FIT Replacements | Replacement of pressure and flow instruments on filters at Ardmore WTP due to condition observed during Condition Assessment rounds | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Electrical | Execution | WW0001203 | Electrical Upgrades Wastewater | FUNDING "BUCKET" for future Electrical Wastewater Projects | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Electrical | Execution | WW0001768 | FY25 Wastewater PS Elec Replacements 1 | Replace switchboards at 11 WWPS | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WA0001711 | Muriwai Source and Treatment Plant |  | 10 - 20 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001438 | Rosedale WWTP PST Enhancement (Fat Collection) | XXX719 - DTROS PST Full scale trial and design (CEPT or AAA) - Energy Neutrality - | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001454 | Mangere WWTP Potable Water Pipework Replacement | Project to be renamed to "DTMAN Inlet Works Recycle Water Upgrade". This project involves installing a new water supply to the screens building at Mangere WWTP including pumping from the effluent channel, contrashear, and piping to the screens at the inlet building. This project will prevent loss of plant due to pressure loss in the WEH supply, and decrease maintenance intervals in clearing of the screens | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001405 | SMUNI - minor replacement/improvements | XXX99 - SMUNI - minor replacement/improvements ($700k/yr) - | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001455 | MOH Regional Fluoride Dosing | MOH Regional Fluoride Dosing WA0001455 The W50 Water Treatment Plant (WTP) is expected to remain operational until the new Waikato A WTP is commissioned in 2034. Under the Health (Fluoridation of Drinking Water) Amendment Act 2021, Watercare must fluoridate the Auckland metro supply (0.7–1 mg/L). A dedicated fluoride dosing system is required at W50 due to consistently low treated water fluoride levels (<0.7 mg/L). Additionally, the W50 WTP lacks resilience, as it cannot supply fluoridated water when the Waikato WTP is offline. This project aims to install a fluoridation system at W50 in compliance with the legislation. | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001714 | Huia WTP Sludge Processing Capacity Improvements | Huia WTP Sludge Processing Capacity Improvements Maintaining production capacity and increasing resilience of the almost 100-year-old existing Huia water treatment plant (WTP) is essential for the business until new infrastructure is built to replace the existing plant. Several recent large storm events indicated that a key bottleneck at the treatment plant is the sludge handling capacity, specifically after storm events. This is due to the higher turbidity levels observed from the inflow stream, which has significantly increased the volume of sludge produced. The aim of this project is to increasing the sludge processing capacity and improving resilience of the solids handling process at the Huia WTP. In so doing this project assesses the options to increasing centrifuge capacity and resilience. It also investigates the viability of addressing the sewer network capacity limitations. | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001817 | FY27 Mangere WWTP Renewals |  | 20 - 30 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001836 | FY27 Rosedale WWTP Renewals |  | 10 - 20 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001133 | Linwood Avenue Pipe Upgrades | The aim of this project is to upgrade the chemical facilities at the Waitakere Water Treatment Plant (WTP) to ensure compliance with the regulations and standards. The upgrade will minimise health and safety risks, improve operability and resilience. a) Aluminium Sulphate (Alum): Construct a new storage and dosing system and decommission the existing system b) Lime: Construct a new slurry makeup, storage, and dosing system, and demolish the existing system. c) Hydrofluorosilicic Acid (HFA): Replace the bulk tank, construct a new storage and dosing system, and decommission the current system. d) Chlorine Gas: Modify the existing drum room by replacing the door and extending the gantry. e) Powdered Activated Carbon (PAC): Add a new big-bag unloading and slurry makeup system while retaining the existing storage and dosing system. f) Polymer: Construct a new storage and dosing system for raw water treatment and modify the existing polymer system. g) Decommissioning and Demolition: Remove outdated systems (Alum, Lime, HFA, and polymer) and reinstate the areas. | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001180 | Gulf Harbour Wastewater Servicing | This project is to allow for population growth for the next 30 years in Gulf Harbour. The project includes building a local new pump station and local rising main | 10 - 20 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001215 | Beach Haven Diversion | This project aims to resolve capacity constraints of the Beach Haven Wastewater Branch Sewer TS10, currently operating over capacity. This will involve construction of a diversion transmission line from Cronin Wastewater Pump Station to Kahika Pumpstation. This project shall provide increased capacity in the network to improve level of service, resilience, and provide for growth. | 20 - 30 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001804 | Hingaia WW Storage Solution | The existing Hingaia wastewater pumping station is already at capacity. The current population projection indicates that additional flow from the future developments will exceed existing capacity of the Hingaia pumping station in the near future and increase the risk of wastewater overflow into the environment. In order to allow for the developments to continue an additional storage capacity needs to be provided until an interim Hingaia pumping station upgrade will be completed. The new storage tanks will provide a temporary solution to service growth in the Southern Growth Area (SGA) until interim upgrade of the existing Hingaia wastewater pumping station will be completed. It will also increase resilience by providing required emergency storage for the interim Hingaia pumping station. | 20 - 30 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001083 | Redoubt PS Upgrade |  | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001385 | Warkworth Western Zone - Boost Pump Station | XXX62 - Western Zone - Boost pump station - | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001492 | Kitchener Rd PS Replacement | XXX576 - Kitchener Rd PS, Pukekohe - Determine optimum size and location for new Anzac zone. Review Jackie's work. - URGENT dependent on Pukekohe West BSP work complete. Pumps old and currently failing to match demand. - | 3 - 10 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001637 | Zita Pumped Zone Reconfiguration |  | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001495 | Mt Hobson PS Upgrade | Mt Hobson PS Upgrade • Pumps nearing end of lifetime and currently not meeting system demand. • Main risks are the current pump failing and the challenges around the constructability phase of project. • Current scope only includes pump station upgrade. Upstream and downstream are out of scope. • SCADA data and modelling results show the pumps are undercapacity for current demand. • Pump upgrade required to meet both current and future demands. | < 3 Million | within panel
FY27 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001756 | Establishment of Permanent Tanker Filling station | Development of a new permanent tanker filling station (TFS) in Huapai to replace the existing temporary TFS at 18 Oraha Rd. The tankers that will be refilled at this station are to service properties in Kumeu, Huapai, and surrounding areas isolated from the water network and reliant on rainwater tanks. | 3 - 10 Million | within panel
FY27 Q1 | Discrete Projects | Discrete Projects | Design | WA0001395 | Takanini 2 Renewal | Business Needs: - The current AC Takanini 2 transmission watermain is in poor condition and requires replacement. - The Takanini WSZ is projected to grow from 10MLD to 17.5MLD over a 50 year planning horizon. This will require the new watermain to be upsized. | 50 - 100 Million | outside panel
FY27 Q1 | Discrete Projects | Discrete Projects | Design | WW0001005 | Howick WW Catchment System Upgrades | Proposed Howick Diversion consisting of a new pump stations and associated network upgrades in Aviemore and Millhouse Parks to provide for growth and mitigate sewer overflows from the Howick interceptor, the Bucklands Beach branch sewer, Pakuranga pump station (DPS028) and local branch sewers. | 30 - 50 Million | outside panel
FY27 Q1 | Discrete Projects | Discrete Projects | Design | WW0001399 | Silverdale West WW Pump Station | The Silverdale West Wastewater Pump Station (WWPS), upstream gravity sewer from Small Rd, and downstream connection to the Milldale Branch Sewer are needed to provide wastewater service and enable the growth of the Silverdale West catchment. | 30 - 50 Million | outside panel
FY27 Q1 | Major Projects | Major Projects | Design | WW0001173 | Stanmore PS & RM Upgrade | This project is to construct a new Stanmore pump station to provide future 100 year capacity linked with a 9km Rising Main between Stanmore pump station and Army Bay Waste Water Treatment Plant. | 100 - 250 Million | outside panel
FY27 Q2 | Asset Upgrades & Renewals | Civil & Construction | Execution | WA0001336 | Fairview Pump Station | Renewal and relocation of Fairview PS. | 30 - 50 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | SS0001069 | Networks PS Electrical Upgrade | Electrical Upgrades at 6 Pump Stations in the Northen Network WWPS | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WA0001730 | STWEL Switchboard Replacement | Urgent replacement of switchboard at Wellsford WTP due to safety and resilience concerns | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WA0001731 | STHEL Standby Generator | Backup generator for Helensville WTP | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WW0001218 | Wastewater Transmission VSD Upgrades | Replace aged Variable Speed Drives at a number of WWPS | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WW0001272 | DPPPW (PS20) Backup Power Supply | Design and installation of grid scale battery to prevent overflows during power outages | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Electrical | Execution | WW0001767 | FY25 Wastewater PS Elec Replacements 2 | Replacement of switchboards at 10 WWPS | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001151 | Owhanake WWTP Upgrade (Stg 2) |  | < 3 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001483 | Rosedale WWTP Inlet Works (Screens/Conveyors) | The Rosedale WWTP Inlet Works (Screens/Conveyors) Project is needed to improve intake capacity and resilience to meet future flow demand. It will also enable future plant upgrades and expansion. | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001441 | Rosedale Buildings #2 Admin/Control | Ops building (WWTP control room and admin) and Maintenance Delivery (including workshops) relocations, plus a new Staff/Visitor's building to reaccommodate various teams currently working in Portacoms onsite. | 20 - 30 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001185 | Unsworth Heights Diversion | This projects aim is to address regular overflows from MH 1224392 that regularly overflows into Alexandra stream which runs adjacent to the assets. The manhole is shallow but the main contributing factor to the overflows are downstream capacity constraints. Solutions are targeted around diversion or improving downstream capacity to alleviate stress on the network and ultimately reduce the number of overflows into the stream thus improving water quality. | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001678 | WIWQIP Avondale Whau CC7A CC7A1 to Miranda Shaft | The project is associated with upgrading CC7A and CC7A1 EOP collector sewers to address current performance issues, provide capacity for growth, and capture combined sewer overflows. | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001482 | Mairangi Bay Gravity Wastewater Sewer Upgrade | Mairangi Bay gravity wastewater sewer upgrade - This project will reduce uncontrolled overflows at manholes upstream of the Jutland St EoP as well as reduce the overflows at the Jutland Street EoP to within its NDC limits. The project involves installing a new 300OD pipeline via trenchless technology and installing 8 new manholes. | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001743 | Sylvia Park Rising Main(s) Rehabilitation | The old sections of the Sylvia Park twin rising mains, comprising various pipe materials, concrete-lined steel, asbestos cement, and reinforced concrete, have experienced several failures, resulting in not only high repair costs but also major disruption of Sylvia Park shopping centre and Mt Wellington Highway. This project will structurally rehabilitate these old rising mains and extend their life for another 50 years. | 10 - 20 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001285 | Warkworth Water Hudson Rd to Matakana Link Rd | WA0001285 - Watermain from Hudson Road WTP upto Matakana Link Road | 3 - 10 Million | within panel
FY27 Q2 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001333 | Market Road Watermain Replacement | Active Project - Do not use WA00001396 | 3 - 10 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Civil & Construction | Design | WA0001398 | Warkworth Northern Reservoir Boost PS & Trnk Mns | WA0001398 - Northern zone reservoir and local boost pump station | 10 - 20 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WA0001732 | FY25 Water PS Elec Replacements 2 | Replace switchboards at three water PS (WPCBL, WPONL, WPRED) Note: WPRED now excluded as already upgraded under a different project | 3 - 10 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WA0001733 | FY25 Water PS Elec Replacements 1 | Replacement of switchboards at three WPS (WPWCR, WPWKE, WPSUN) Note: WPSUN now excluded as already replaced under another project. | 3 - 10 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Electrical | Execution | WA0001735 | STWKO VSD Replacements | Replace small VSDs at Waikato WTP due to age and obsolescence | < 3 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001449 | Mangere WWTP New admin building | XXX14 - New admin building - separation of production from public - H&S, security driven - | 30 - 50 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001798 | Waiuku WW Network diversion | This project involves installing two diversions in the Waiuku Wastewater Network to address capacity constraints in the ageing infrastructure of the wastewater network at Waiuku golf course. | < 3 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001397 | Mangere Watermain High Volume Flushing Valve | Link between Hunua 3 and 4 via Mangere WM - - enables redundancy to the whole of Mangere zone. Needs flushing valves to redirect flows. | < 3 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001492 | Kitchener Rd PS Replacement | XXX576 - Kitchener Rd PS, Pukekohe - Determine optimum size and location for new Anzac zone. Review Jackie's work. - URGENT dependent on Pukekohe West BSP work complete. Pumps old and currently failing to match demand. - | 3 - 10 Million | within panel
FY27 Q3 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001526 | Waikumete Pump Station (Sunnyvale PS) | Implementation of a boosted supply zone via a new Pump Station to be constructed next to the Waikumete Reservoir. | 3 - 10 Million | within panel
FY27 Q3 | Discrete Projects | Discrete Projects | Design | WA0001025 | Wellsford Water Treatment Upgrade | Wellsford Water Treatment Plant Upgrade The Wellsford WTP Upgrade is a critical infrastructure project led by Watercare to replace the aging 1960s plant and provide a future-proofed, compliant, and resilient water supply to Wellsford and Te Hana. The upgraded plant will increase treatment capacity from 1,400 m³/day to 2,800 m³/day (with provision for future expansion to 4,084 m³/day), ensuring long-term compliance with the Drinking Water Standards for New Zealand (DWSNZ) and supporting anticipated population growth through 2056. The project includes a new site layout, land acquisition, additional geotechnical investigations, updated process design (including disinfection and sludge management), and integration of backwash waste handling solutions. | 30 - 50 Million | TBC
FY27 Q3 | Discrete Projects | Discrete Projects | Execution | WA0001042 | Waiuku Water Treatment Upgrade | This project will deliver a new centralized water treatment plant for Waiuku at 11 Cornwall Rd which will consolidate existing bores located at four different locations in the area. Treated water will then be pumped to two storage reservoirs at 1471 Waiuku Rd and one at 83 Victoria Ave. Approximately 3,500 meters each of new raw and treated water pipelines will connect the new treatment plant to the existing bores and reservoirs. As part of this project, three existing WTPs will be decommissioned, with the bores and reservoirs integrated into the new system. The outcomes sought from delivering the project are to increase WTP capacity, ensure compliance with relevant regulations, and improve reliability to the desired level of service. | 30 - 50 Million | outside panel
FY27 Q3 | Discrete Projects | Discrete Projects | Execution | WA0001109 | Onehunga WTP PFAS & Second Barrier | Upgrade of existing 25MLD Onehunga Water Treatment Plant to: - Comply with regulatory standards (i.e. PFAS, fluoridation) - Improve water supply system resilience - Replace assets at end of service life Comprises of the following scope items: - New treatment assets (GAC system, UV, polymer) - New electrical and control systems - New mechanical systems (pumps, valves) - Associated civil and structural works (buildings, foundations, roading, underground services) - Modification of existing assets - Commissioning and decommissioning - Design, investigations and statutory approvals | 30 - 50 Million | outside panel
FY27 Q3 | Discrete Projects | Discrete Projects | Execution | WA0001365 | Devonport 2 Watermain Replacement | WA0001365 - Devonport 2 watermain - urgent replacements Approximately 4.5 km of 300mm AC pipeline to be replaced/upgraded. | 30 - 50 Million | within panel
FY27 Q3 | Discrete Projects | Discrete Projects | Execution | WA0001619 | Tamaki Precinct Water | The works support redevelopment of the Tamaki Precinct to enable approximately 14,100 healthy homes over the next 50 years. The project involves the installation of 5.3 km of local network watermains within the road reserve across two key alignments in the Tamaki Precinct, to service growth and intesification driven by KO Tamaki & Specialist vehicle setup for developments (TRC): Northern Alignment: 4.1 km of pipelines fed from the St Johns Reservoir, serving the Glen Innes zone. Southern Alignment: 1.2 km of pipeline that serves the Panmure zone and is fed from the Bridge Street Bulk Supply Point. | 50 - 100 Million | outside panel
FY27 Q3 | Discrete Projects | Discrete Projects | Execution | WW0001446 | Paerata Wastewater Servicing | Upgrade of the existing Te Paea Pump Station, construction of a new Paerata Pump Station, and installation of a rising main linking both to the Isabella North Pump Station. The works will improve capacity, reliability, and future-proof wastewater conveyance for growth in the area. | 50 - 100 Million | outside panel
FY27 Q3 | Major Projects | Major Projects | Execution | WA0001241 | Waikato A Raw Water Intake | This project includes the construction of a new Raw Water Pump Station for the future Waikato A WTP. The W50 floating pump station can then be removed from the Waikato River. The new Waikato A RWPS will be connected to the existing W50 RM to supply the W50 water treatment facility. | 100 - 250 Million | outside panel
FY27 Q4 | Asset Upgrades & Renewals | Civil & Construction | Execution | WA0001398 | Warkworth Northern Reservoir Boost PS & Trnk Mns | WA0001398 - Northern zone reservoir and local boost pump station | 10 - 20 Million | within panel
FY27 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001711 | Muriwai Source and Treatment Plant |  | 10 - 20 Million | within panel
FY27 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001151 | Owhanake WWTP Upgrade (Stg 2) |  | < 3 Million | within panel
FY27 Q4 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001454 | Mangere WWTP Potable Water Pipework Replacement | Project to be renamed to "DTMAN Inlet Works Recycle Water Upgrade". This project involves installing a new water supply to the screens building at Mangere WWTP including pumping from the effluent channel, contrashear, and piping to the screens at the inlet building. This project will prevent loss of plant due to pressure loss in the WEH supply, and decrease maintenance intervals in clearing of the screens | 3 - 10 Million | within panel
FY27 Q4 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001417 | Pleasant Rd PS Replacement | WW0001417 - The Pleasant Road Pump Station (PRPS) Replacement project addresses the end-of-life renewal of a critical water infrastructure asset serving West Auckland. Originally designed to boost flow from the Huia 2 Watermain to the Waitakere Reservoir, the station was repurposed in 2023 following flood-related damage to instead supply the Highland Avenue Bulk Supply Point (BSP). This change eliminated its dual-supply function, reducing network resilience. This project will deliver feasibility and concept design for: A new dual-pump configuration within a single building—one set dedicated to the Highland Ave BSP, and one to the Waitakere Reservoir via the Waitakere 1 Watermain. Enhanced supply resilience and operational flexibility during network failures or planned outages. Capacity upgrades to support future growth and shutdowns at the Waitakere WTP and raw watermain. Consideration of new site acquisition due to existing spatial constraints. The upgrade will restore critical redundancy, support ~15,000 residents, and strengthen West Auckland's water supply resilience. | 10 - 20 Million | within panel
FY27 Q4 | Major Projects | Major Projects | Design | WW0001573 | Pukekohe Upgrade Stage 3 (Pe Plus 30 0000) | Pukekohe upgrade stage 3 (PE plus 30,0000) This project will increase the capacity of the Pukekohe WWTP by about 30,000PE. | 100 - 250 Million | outside panel
FY28 Q1 | Asset Upgrades & Renewals | Electrical | Execution | WW0001766 | DTMAN Switchboards Replacement FY25 | Replacement of six HV and six LV switchboards at Mangere WWTP | 10 - 20 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WA0001486 | Helensville WTP Process Improvements | XXX590 - Helensville WTP Capacity Upgrade - To add Production capacity to the Helensville township to enable development | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Design | WW0001440 | Rosedale WWTP Anammox Side Stream | XXX721 - DTROS Anammox side stream design and implementation - | 10 - 20 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001487 | Warkworth WTP Capacity Upgrade - Stage 1 | This project is to increase the output of the WTP from ~3MLD to ~4.3MLD. | 10 - 20 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WA0001521 | Warkworth Southern Zone - Sanderson Rd WTP Upgrade | XXX648 - Southern Zone - Boost pump station - at sanderson Rd WTP. - | < 3 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001438 | Rosedale WWTP PST Enhancement (Fat Collection) | XXX719 - DTROS PST Full scale trial and design (CEPT or AAA) - Energy Neutrality - | < 3 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001449 | Mangere WWTP New admin building | XXX14 - New admin building - separation of production from public - H&S, security driven - | 30 - 50 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater & Water Treatment Plants | Execution | WW0001837 | FY28 Rosedale WWTP Renewals |  | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Design | WW0001452 | Opaheke Wastewater Servicing - Trunk Rising | XXX25 - Opaheke Wastewater Servicing - trunk RM main - Opaheke to Hingaia PS. Tie in with NZTA timing Parker Estate Bridge. | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001133 | Linwood Avenue Pipe Upgrades | The aim of this project is to upgrade the chemical facilities at the Waitakere Water Treatment Plant (WTP) to ensure compliance with the regulations and standards. The upgrade will minimise health and safety risks, improve operability and resilience. a) Aluminium Sulphate (Alum): Construct a new storage and dosing system and decommission the existing system b) Lime: Construct a new slurry makeup, storage, and dosing system, and demolish the existing system. c) Hydrofluorosilicic Acid (HFA): Replace the bulk tank, construct a new storage and dosing system, and decommission the current system. d) Chlorine Gas: Modify the existing drum room by replacing the door and extending the gantry. e) Powdered Activated Carbon (PAC): Add a new big-bag unloading and slurry makeup system while retaining the existing storage and dosing system. f) Polymer: Construct a new storage and dosing system for raw water treatment and modify the existing polymer system. g) Decommissioning and Demolition: Remove outdated systems (Alum, Lime, HFA, and polymer) and reinstate the areas. | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001180 | Gulf Harbour Wastewater Servicing | This project is to allow for population growth for the next 30 years in Gulf Harbour. The project includes building a local new pump station and local rising main | 10 - 20 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001390 | Clevedon WW Stage 3 | Future wastewater rising main from Clevedon to the Takanini Branch Sewer, plus vacuum pipeline (pink pipe) through Conmara development site. | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Wastewater Pipeline Renewals | Execution | WW0001678 | WIWQIP Avondale Whau CC7A CC7A1 to Miranda Shaft | The project is associated with upgrading CC7A and CC7A1 EOP collector sewers to address current performance issues, provide capacity for growth, and capture combined sewer overflows. | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001397 | Mangere Watermain High Volume Flushing Valve | Link between Hunua 3 and 4 via Mangere WM - - enables redundancy to the whole of Mangere zone. Needs flushing valves to redirect flows. | < 3 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Design | WA0001503 | WWs West Coast Road Cross Connection-NH 2 To NH1 | 0 | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001130 | Hingaia Watermain East/West | The Southern Growth Area (SGA) encompassing Hingaia, Drury, Auranga, Opaheke and Paerata is due to undergo significant growth over the next 20 years. Approximately 6,000 lots (18000 PE)for the SGA are predicted to be developed by 2025. This watermain is required to be completed and in service before the SGA development reaches 5,600 lots (~2025), to ensure levels of service can be maintained in the area. Once complete, the HEW watermain will provide two feeds to the Hingaia Peninsula and Auranga developments providing network resilience through redundancy. | 10 - 20 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001321 | Clevedon Water Stage 3 | Future Reservoir and access road in Clevedon. | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001385 | Warkworth Western Zone - Boost Pump Station | XXX62 - Western Zone - Boost pump station - | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001416 | Mission Heights PS - Upgrade | XXX124 - Mission Heights PS - Upgrade - - 15 Years old - need to review Brendon's work | < 3 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001503 | WWs West Coast Road Cross Connection-NH 2 To NH1 |  | 3 - 10 Million | within panel
FY28 Q1 | Asset Upgrades & Renewals | Water Pipeline Renewals | Execution | WA0001637 | Zita Pumped Zone Reconfiguration |  | < 3 Million | within panel
FY28 Q1 | Discrete Projects | Discrete Projects | Design | WA0001037 | Woodlands Park Reservoir & Pipelines | A new water treatment plant is to be constructed to replace the current Huia WTP which is nearing the end of its plant lifetime. The new Huia WTP will require reservoirs to be installed to increase the short-term peak capacity of the water supply. The scope of this project revolves around the installation of the reservoirs, and therefore requires: • Installation of two 25,000 m3 reservoirs and connecting pipework | 30 - 50 Million | outside panel
FY28 Q1 | Discrete Projects | Discrete Projects | Design | WW0001175 | Orewa to Stanmore WW Trunk Network Upgrade |  | 50 - 100 Million | within panel
FY28 Q1 | Major Projects | Major Projects | Design | WA0001123 | WWS Upper Nihotupu Raw Watermain Replacement | This project aims to identify the feasibility and preferred option for replacement of the Upper Nihotupu Raw Watermain. | 100 - 250 Million | outside panel